## Sheet1
ID | Phase | Task | Start Date | End Date | Duration | Dependency
T1 | Planning | Define scope and objectives | 2025-06-01 | 2025-06-02 | 2 | - | 45809 | 45857
T2 | Planning | Assign roles and responsibilities | 2025-06-03 | 2025-06-04 | 2 | T1
T3 | Planning | Select tools (GitHub, Jira) | 2025-06-05 | 2025-06-07 | 3 | T2
T4 | Risk Assessment | Perform vulnerability scanning | 2025-06-08 | 2025-06-11 | 4 | T3
T5 | Risk Assessment | Conduct threat modeling and analysis | 2025-06-12 | 2025-06-15 | 4 | T4
T6 | Risk Assessment | Prioritize identified risks | 2025-06-16 | 2025-06-21 | 6 | T5
T7 | Mitigation | Implement Multi-Factor Authentication (MFA) | 2025-06-22 | 2025-06-26 | 5 | T6
T8 | Mitigation | Update and configure firewall rules | 2025-06-27 | 2025-07-01 | 5 | T7
T9 | Mitigation | Conduct cybersecurity training for employees | 2025-07-02 | 2025-07-05 | 4 | T8
T10 | Monitoring | Set up continuous threat detection tools | 2025-07-06 | 2025-07-12 | 7 | T9
T11 | Monitoring | Test incident response procedures | 2025-07-13 | 2025-07-19 | 7 | T10